## Project Schedule
DOCUMENT VERSION: 1.0
PROJECT NAME | Cloud Counselage Student Data Analysis
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | .ipynb code, video, project charter, SRS document, WBS, Project plan, Raid Logs
PROJECT SCOPE | Attributes, Data cleaning & preprocessing, exploratory data analysis, data visualization
PROJECT START DATE | 2023-08-01
PROJECT END DATE | 2023-09-30
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | Project Kick off |  | 2023-08-01 | 2023-08-02 | 2 | COMPLETED
1.1 | Understand project objectives and scope
1.2 | Understand reporting structure and communication channels
1.3 | Define project timelines and roles
2 | Requirement Analysis |  | 2023-08-03 | 2023-08-10 | 8 | COMPLETED
2.1 | Gather data analysis requirements from stakeholders
2.2 | Analyse the detailed requirements document
3 | Data Preprocessing |  | 2023-08-11 | 2023-08-26 | 15 | COMPLETED
3.1 | Cleanse and validate data for quality and consistency
3.2 | Handle missing data
3.3 | address outliers and anomalies
3.4 | Create a cleaned dataset for analysis
4 | Exploratory Data Analysis (EDA) |  | 2023-08-27 | 2023-09-16 | 20 | COMPLETED
4.1 | Visualize data distribution and patterns
4.2 | Identify correlations and relationships among variables
4.3 | conduct summary and descriptive statistics
4.4 | Generate exploratory plots and charts
5 | Data Visualization |  | 2023-09-17 | 2023-09-30 | 16 | COMPLETED
5.1 | Choose appropriate visualization tools (e.g. Matplotlib, Seaborn)
5.2 | Create visualizations as per requirements
5.3 | Ensure visualizations align with project objectives
5.4 | Communicate insights effectively through visuals
6 | Report Generation |  | 2023-09-17 | 2023-09-30 | 16 | COMPLETED
6.1 | Compile analysis results and insights
6.2 | Create a comprehensive project report
6.3 | Include visualizations, findings and recommendations
6.4 | Review and edit the report for clarity and coherence
7 | Project Review |  | 2023-09-17 | 2023-09-30 | 16 | COMPLETED
7.1 | Evaluate progress and milestones
7.2 | Gather feedback and lessons learned
7.3 | Assess project outcomes against initial objectives
7.4 | Identify areas of improvement and optimization
8 | Closure |  | 2023-09-17 | 2023-09-30 |  | COMPLETED
4 Closure